## Development
Story Cards |  |  |  | Development
Story ID | Priority | Story points | Hour Equivalent | Team Structure | Number of People | Hourly wage per person | Hours per day | Daily wage /person | Cost per day
1 | C | 1 | 8 | Developers | 3 | 35 | 8 | 280 | 840
2 | M | 1 | 8 | UI Designer | 1 | 52 | 8 | 416 | 416
3 | M | 1 | 8 | Tester | 1 | 25 | 8 | 200 | 200
4 | M | 2 | 16 | Business Analyst | 1 | 62 | 8 | 496 | 496
5 | M | 1 | 8 | Project Manager | 1 | 63 | 8 | 504 | 504
6 | S | 1 | 8 |  |  |  |  | 1896 | 2456
7 | M | 1 | 8
8 | M | 2 | 16 | Estimated Development cost | 103152
9 | S | 4 | 32
10 | M | 1 | 8 | Development Overheads
11 | M | 2 | 16 | Tasks | Weeks | Cost per week | Total Cost
12 | M | 4 | 32 | Designing website | 4 | 2912 | 11648
13 | S | 2 | 16 | Load Testing | 1 | 1400 | 1400
14 | C | 1 | 8 | Final Testing | 1 | 1400 | 1400
15 | S | 1 | 8
16 | M | 1 | 8 | Estimated Development Overhead cost | 14448
17 | C | 4 | 32
18 | M | 4 | 32
19 | S | 1 | 8 | Estimated Dollar Cost
20 | M | 1 | 8 | Total Project Cost | 117600
21 | C | 4 | 32
22 | C | 1 | 8
23 | C | 1 | 8
|  | 42 | 336

## Cost-Benefit Analysis
Cost - Benefit Analysis
Total Project Cost | 117600
Benefits $
*Assuming 20% sensitivity |  |  |  |  | Minimum | Likely | Maximum
$117,600 x 1.2 | 141120 |  |  |  | 94080 | 117600 | 141120
$117,600 x 0.8 | 94080 | Cost $ | Maximum | 141120 | -47040 | -23520 | 0
|  |  | Likely | 117600 | -23520 | 0 | 23520
|  |  | Minimum | 94080 | 0 | 23520 | 47040
Min Cost | 94080
Likely Cost | 117600
Max Cost | 141120