## Sprint 2
Story Cards |  |  |  |  | Development
Story ID | Priority | Story points | Hour Equivalent | Sprint | Team Structure | Number of People | Hourly wage per person | Hours per day | Daily wage /person | Cost per day
2 | M | 1 | 8 | 2 | Developers | 3 | 35 | 8 | 280 | 840
3 | M | 1 | 8 | 2 | UI Designer | 1 | 52 | 8 | 416 | 416
4 | M | 2 | 16 | 2 | Tester | 1 | 25 | 8 | 200 | 200
5 | M | 1 | 8 | 2 | Business Analyst | 1 | 62 | 8 | 496 | 496
7 | M | 1 | 8 | 2 | Project Manager | 1 | 63 | 8 | 504 | 504
18 | M | 4 | 32 | 2 |  |  |  |  | 1896 | 2456
|  | 10 | 80
[5 empty] | Estimated Development | 24560
Development Overheads
[5 empty] | Tasks | Weeks | Cost per week | Total Cost
[5 empty] | Designing website | 4 | 2912 | 11648
[5 empty] | Load Testing | 1 | 1400 | 1400
[5 empty] | Final Testing | 1 | 1400 | 1400
[5 empty] | Estimated Development | 14448
Estimated Dollar Cost
[5 empty] | Total Project Cost | 39008